## Sheet1
| Description | Deadline | Tasks | Deliverable | Allocation
D4.1-1 | AI/ML detection Develop methods for detecting embedded AI/ML in software packages following three major scenarios: AI/ML use is reported, AI/ML use is falsely claimed, AI/ML use is obfuscated. Output: AI/ML detection tool as part of the ML/AI software Security (MLAS) software suite. Utilization plan drafted. | 2023-02-01 | D4.1-1.1: Define what knid of scenarios can be considered as AI/ML is used in software packages. | Output: "Ground-truth" of AI/ML usgae in software. 01.11.2022-15.12.2022 | Hongsheng (Data61); Deakin: Yanjun, Jack Li, Chang-Tsun Li,
|  |  | D4.1-1.2: Develop semi-supervised or supervised learning techniques for detecting embedded AI/ML in software packages. | Output: Detection method. 15.12.2022-01.02.2023 | Hongsheng (Data61); Deakin: Yanjun, Jack Li, Chang-Tsun Li;
|  |  | D4.1-1.3: Evaluate the proposed techniques and report the metrics of accuracy (i.e., AI/ML use is reported), true negtive rate (i.e., AI/ML use is falsely claimed), and true positive rate (i.e., AI/ML use is obfuscated). | Output: Performance evaluation of the proposed method. 15.12.2022-01.02-2023 | Hongsheng (Data61); Deakin: Yanjun, Jack Li, Chang-Tsun Li;
D4.1-2 | AI/ML dependency assessment Identify the significant metadata types and build AI/ML Software Bill of Materials (SBOM) in AI/ML software systems. Develop methods to identify and build dependency graphs, including dependency from data, access control and algorithmic aspects. Output: AI/ML dependency assessment tool as part of the MLAS software suite. IDE plug-in version of the tools. Dataset delivery to WP2. Utilization plan completed. End user Engagement: Transfer of the MLAS to end users for further tests. | 2023-05-01 | D4.1-2.1: Build dictionaries of keywords extracted from popular AI/ML libraries. | Output: Keyword sets of AI/ML libraries covering data, access and algorithm aspects 01.02.2023-15.03.2023 | Hongsheng (Data61), Research Fellow (CSU)
|  |  | D4.1-2.2: Develop appropriate methods and tools for detecting software components dependent on an external AI/ML services. | Output: AI/ML dependency assessment tool as part of the MLAS software suite. IDE plug-in version of the tools. 01.03.2023-15.04.2023 | Hongsheng (Data61), Research Fellow (CSU)
|  |  | D4.1-2.3: Produce flow and dependency graphs of the detected AI/ML components and capture how these components affect the overall software system. | Output: Flow and dependency graphs of the detected AI/ML components on a large scale. Dataset delivery to WP2. 01.04.2023-01.05.2023 | Hongsheng (Data61), Research Fellow (CSU)
D4.1-3 | AI/ML penetration testing Identify gaps in the security of AI/ML and develop novel penetration methods to fill the gaps. Develop methods to orchestrate the novel and existing tools and perform a penetration test on AI/ML-enabled software, covering the dependencies. This phase will also investigate methods to formulate effective testing procedures against adversarial attacks. Output: AI/ML penetration testing tool as part of the MLAS software suite. Utilization plan reviewed and agreed. | 2023-08-01 | D4.1-3.1: Analyse AI/ML against various attacks, e.g., property /membership inference attacks, privacy breaches, and data poisoning. | Output: Gaps in the security of AI/ML. 01.08.2023-15.09.2023 | Hongsheng (Data61); Deakin: Yanjun, Jack Li, Chang-Tsun Li;
|  |  | D4.1-3.2: Develop methods to evaluate AI/ML software security against attacks, utilizing the novel and existing tools. | Output: Novel penetration methods and testing tools. 01.09.2023-15.10.2023 | Hongsheng (Data61); Deakin: Yanjun, Jack Li, Chang-Tsun Li;
|  |  | D4.1-3.3: Perform a penetration test on AI/ML-enabled software. | Output: An empirical study on AI/ML-enabled software security. 15.10.2023-01.11.2023 | Tien-Fu Lu (UoA)
D4.1-4 | Enhanced AI/ML penetration testing Enhancing the penetration testing capability with intelligence support using TTP. Extend the scope from testing AI/ML software packages to testing MLaaS (Machine learning as a service) systems. Output: Enhanced AI/ML penetration testing tool as part of the MLAS software suite. IDE plug-in version of the tool. Dataset delivery to WP2. Utilization plan executed. End user Engagement: Transfer of the MLAS to end users for further tests. | 2023-11-01 | D4.1-4.1: Investigate the potential attack within the context of the software systems, AI/ML vendors and AI/ML dependencies to assess potential consequences, likelihoods and impacts | Output: An analysis report of potential attacks against AI/ML software and MLaaS. 01.11.2023-01.12.2023 | Tien-Fu Lu (UoA)
|  |  | D4.1-4.2: Develop discriminative and generative predictors to security attacks, extending the scope of penetration testing to MLaaS. | Output: Enhanced AI/ML penetration testing tool as part of the MLAS software suite. IDE plug-in version of the tool. 01.12.2023-15.01.2024 | Tien-Fu Lu (UoA)
|  |  | D4.1-4.3: Perform a penetration test on MLaaS. | Output: An empirical study on MLaaS security. 15.01.2024-01.02.2024 | Tien-Fu Lu (UoA)
D4.2-1 | Risk assessment Develop methods to identify security and privacy risks introduced by AI/ML into the software system. Output: Risk assessment tool as part of the MLAS. Utilization plan revisited and revised. | 2024-02-01 | D4.2-1.1: Conduct comprehensive survey on different kinds of security and privacy risks of AI/ML models | Output: The type of security and privacy risks of AI/ML models. | Hongsheng (Data61)
|  |  | D4.2-1.2: Rank and select the appropriate security and privacy attacks that are suitable for identifing and quantifing risks of AI/ML in the context of software system. | Output: Baselines of the security and privacy risks. | Hongsheng (Data61), Chelsea Liu (UoA)
|  |  | D4.2-1.3: Build a framework to evaluate the security and privacy risks of AI/ML models | Output: Risk assessment tool of the MLAS | Hongsheng (Data61), Chelsea Liu (UoA)
D4.2-2 | Enhanced risk assessment Enhancing risk assessment method by experimenting with shallow and deep models. Develop ML-based methods to assess AI/ML security and privacy introduced into the software system at installation, software update or model update/tuning. Output: Enhanced risk assessment tool as part of the MLAS software suite. IDE plug-in version of the tool. Dataset delivery to WP2. Utilization plan executed. End user Engagement: Transfer of the MLAS to end users for further tests. | 2024-05-01 | D4.2-2.1: Identify the important and popular AI/ML models (including both shallow and deep models) used in software system | Output: The target AI/ML for evaluation | Hongsheng (Data61), Chelsea Liu (UoA)
|  |  | D4.2-2.2: Develop ML-based methods to evaluate the security and privacy risks of the target models | Output: ML-based methods for evaluation. | Hongsheng (Data61), Chelsea Liu (UoA)
|  |  | D4.2-2.3: Build an enhanced risk assessment framework using the ML-based methods to assess AI/ML components in the software system at installation, software updates, and model update/tuning. | Output: Enhanced risk assessment tool as part of the MLAS software suit. | Hongsheng (Data61), Chelsea Liu (UoA)
D4.2-3 | Static risk mitigation Evaluate existing (e.g., robustness, perturbation, etc.) and develop new static techniques to mitigate risks due to vulnerabilities introduced into software packages by its ML components. Output: Static risk mitigation tool as part of the MLAS software suite. Utilization plan revisited and revised. | 2024-08-01 | D4.2-3.1: Conduct a comprehensive survey on exsiting defense techniqes that can mitigate the vulnerabilities of AI/ML models | Output: The defense techniques used for evulation | Hongsheng (Data61), Research Fellow (CSU)
|  |  | D4.2-3.2: Selelct appropriate and promising defense techniques and evaluate their mitigation performance. | Output: Baselines of existing defense techniques | Hongsheng (Data61), Research Fellow (CSU)
|  |  | D4.2-3.3: Develop new static techniques that can fill the gap of existing defense techniques on mitigating the vulnerability of ML components. | Output: Comprehensive static risk mitigation tool as part of the MLAS software suite | Hongsheng (Data61), Research Fellow (CSU)
D4.2-4 | Dynamic risk mitigation Develop methods for runtime risk detection and mitigation. Develop methods for dynamic risk detection through watchdog, forensics and logging mechanisms, including hardware perspective. Develop methods for runtime risk mitigation by enforcing ML operate within normal boundaries within software packages and MLaaS systems. Output: Dynamic risk mitigation tool as part of the MLAS software suite. IDE plug-in version of the tool. Integration within WP3 Plug-in solution and WP1 Supply Chain Security (SCS) software stack. Final dataset delivery to WP2. Utilization plan executed. End user Engagement: Transfer of the MLAS to end users for full tests. | 2024-11-01 | D4.2-4.1: Identify what security and privacy risks the software system will face during runtime. Develop detection and mitigation method for the vulnerability of the software system during the runing time | Output: detection and mitigation method for the vulnerability of the software system during the runing time | Hongsheng (Data61), Tien-Fu Lu (UoA)
|  |  | D4.2-4.2: Conduct a systematic evaluation of AI/ML security from a hardware perspective, identifying possible software attacks from real-world hardware platforms. | Output: Software attacks from the hardware perspective | Hongsheng (Data61), Tien-Fu Lu (UoA)
|  |  | D4.2-4.3: Develop methods for dynamic risk detection and mitigation for runtime of the software system | Output: Dynamic risk mitigation tool as part of the MLAS software suite | Hongsheng (Data61), Tien-Fu Lu (UoA)