## Slide 1: SOCRATES WP4: Building secure AI/ML software
Hongsheng Hu, Data61
Jason Xue, WP4 lead, Data61
QUARTERLY REVIEW (Q1 22/23)

## Slide 2: Overview
  Project Deliverables
  Start: December 01, 2022
  End: December 01, 2024
  Project Aim: Building secure AI/ML software
  This project will identify and mitigate security risks of AI component in software. Specifically, we will look at the following tasks:
  Detect AI/ML component in software
  Penetration testing of AI/ML component
  Risk assessment of AI/ML component
  Risk mitigation of AI/ML component
  Note: each task can be divided into two sub-tasks
Deliverable | Due Date | Complete
Extensive team discussion | Q1 2023 | Finished
Product prototype file and UI interface | Q4 2023 | In progress
Test versions and release candidates | Q2 2024 | To be done
Full version and documentation | Q4 2024 | To be done

## Slide 3: Deliverables completed this quarter
  Task allocation table (Feb 07, 2023)
    This table allocates the roles of team members, determines project goals and the scope of the project, and describes the project technology.
    Through extensive team discussion, the task table was well created.
    Tangible outputs: excel allocation table
  Collection of OSS packages (Feb 07, 2023)
    This collection contains open-source software (OSS) packages that use AI/ML component.
    Through keyword matching and some other NLP techniques on package descriptions, OSS packages were well collected.
    Tangible outputs: link of the OSS packages and an excel table describes each collected OSS

## Slide 4: Other deliverables in progress
  Framework of the system (August 01, 2023)
    This framework describes system requirements and identify project technologies.
    Through extensive internal team discussion, an initial framework has been created.
    Tangible outputs: a detailed report describes the framework of the system.
  Research output (November 01, 2023)
    A research paper about fairness of AI/ML model and a survey paper of sustainable software engineering in AI
    Through extensive internal and external discussion, the research idea and framework of the survey have been proposed.

## Slide 5: Challenges
  Team members with different research background
    Impact on progress: difficult to allocate the roles of team members
    Proposed solution: we have weekly internal meetings to split the project tasks and bi-weekly external meetings to distribute each task to different team members.
  Too many OSS packages for selection
    Impact on progress: difficult to collect appropriate OSS packages
    Proposed solution: we leverage expert human knowledge to manually extract some OSS and NLP techniques to speed up the collection process for extracting more OSS.

## Slide 6: Deliverables due next quarter
  Assessment of AI/ML component in OSS
    This assessment will test whether AI/ML component in OSS is secure or not
    This is on track because we have clearly identified the project technologies.
    We may focus on some particular security aspects like fairness of AI/ML to avoid competing IP issue
  Research paper drafts
    The paper drafts including a research paper about fairness in AI/ML model and a survey paper of sustainable software engineering
    This is on track because we have proposed the research idea and the survey framework

## Slide 7: Use of Project outputs this quarter
  Use by the Research Organisation Participants
    We are creating two research paper drafts. After publication (if the submission goes well), the two paper can attract attention from research organization and get impact.
  Use by End-User Participants
Has been discussed within Data61
  Use by Others (non-participant end-users, third parties etc.)
Not available in this stage